## Sheet1
| Action | Week Start | 2019-11-25 |  |  |  |  | 2019-12-02 |  |  |  |  | 2019-12-09 |  |  |  |  | 2019-12-16
|  | % Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
|  | Work Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Research | SEO and market competitors, font, color theme, logos | 100% | Week 1 1: Build Time; Week 2 6: Completed; Week 3 11: Debug & Troubleshoot
Code | Home Page | 15% | Week 2 6: Build Time; Week 3 13: Completed
| Our Hikes | 15% | bar: Week 2 6 to Week 3 15
| Our Guides | 15% | Week 3 11: Build Time; Week 4 16: Completed
| Sustainability | 0% | bar: Week 3 11 to Week 4 16
| FAQ | 0% | bar: Week 3 11 to Week 4 16
Test | Testing on a variety of devices | 0% | Week 3 14: Build Time; Week 4 19: Completed